## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
Epic: Donation Request Management
Update Needed Items: As a U-Fund Manager, I want to edit needed item postings so that urgency ratings are up to ate as well as item specifics. | Given a need's values are changed to other valid values when I edit a need then the helpers can immediately view the updated version. | Pass | JW 10/21/2024
Post Needed Items: As a U-Fund Manager, I want to post needed items and how urgent they are so that a Helper can donte to the society. | Given I have a new need and populate it correctly, when I post a need then the Helpers can view that need. | Pass | JW 10/21/2024
Remove Needed Items: As a U-Fund Manager, I want to delete needed items so that items the company no longer wants do not show up for the Helpers as an option. | Given a need is no longer needed, when I delete a need then the Helpers can no longer view that need. | Pass | JW 10/21/2024
Epic: Helper Donations
Check Out Donation Needs: As a Helper, I want to check out the donation needs in my basket so that the donations can go to the company. | Given I have some need(s) in my basket, when I check out then I expect to have funds transferred to my selected needs. | Pass | KVB 10/21/2024
| Given I have some needs in my basket, when I check out then I expect my basket to become empty. | Pass | KVB 10/21/2024
Remove Donation Needs From Basket: As a Helper, I want to remove donation needs from my basket so that I can choose not to donate them if I am no longer interested. | Given I have some need(s) in my basket, when I remove them from my basket then I don't donate to that need. | Pass | RR 10/21/2024
View Basket Needs: As a Helper, I want to be able to see the needs that are currently in my basket. | Given a user exists, when they choose to view their basket then they can see the needs in their basket. | Pass | MK 10/21/2024
Add Donation Needs to Basket: As a Helper I want to add donation needs to my basket so that I can consider which ones to donate the funds for. | Given some need exists, when I view it then I expect to be able to add it to my basket. | Pass | MK 10/21/2024
| Given a need is already in my basket, when I add it to my basket then I expect its quantity to be incremented. | Pass | KVB 10/21/2024
Epic: Web Application
Seach Needs: As a Helper or Manager I want to enter a search in my browser so that I can see the needs that exist. | Given some needs exist (that match my query), when I enter text in the search box and hit enter then I expect to see a list of matching needs. | Pass | RR 10/21/2024
| Given Needs exist but none that match my query, when I enter a search in the browser then I will see a notification that no needs match my search. | Pass | RR 10/21/2024
| Given no needs exist, when I enter a search in the browser then when I search I will be notified that no needs match my search. | Pass | RR 10/21/2024
View Single Needs: As a Helper I want to be able to view the details of a specific need in the cupboard. | Given a need exists, when I click on a need in the frontend then I see additional information about that need. | Pass | RR 10/21/2024
Visit Webpage: As a Helper I want to be able to visit the U-Fun webpage so that I can fund the organization. | Given I want to see the U-Fund webpage, when I enter the U-Fund API then I expect to see the U-Fund webpage. | Pass | JW 10/21/2024
Epic: Simple Auth
Manager Login: As a U-Fund Manager, I want to be able to log in by entering "admin" in the login field so that I can access my Manager account. | Given I want to log in as a Manager, when I log in with the "admin" username then I can manage the account as a Manager. | Pass | KVB, 10/21/ 2024
Helper Login: As a Helper, I want to be able to log in by entering a previously saved username or by creating a new account when I enter a new username, so that I can access my Helper account and see my saved data. | Given an account exists with my username, when I log in with that username then I can see my own data. | Pass | KVB, 10/21/ 2024
| Given an account does not exist with my username, when I log in with that username then it creates a new blank account with that username and I save my own data. | Pass | JW, 10/21/2024
Other:
ISOLATED STORY: Responsive UI: As a Helper I want to be able to view the page cleanly on multiple screen sizes so that it's easy to use the app on all my devices. | Given I'm on a certain size screen when I open the app then it will be rendered cleanly and take up a reasonable amount of space. | Pass | MK 10/21/2024
ISOLATED STORY: Fuzzy Search: As a Helper or Manager when I search for a need then I expect it will appear for any similar search (not just exact searches). | Given one or more needs exist with text, when I search for that text with other capitalization then I will see those needs as search results. | Pass | MK 10/21/2024
| Given no needs exist with given text, when I search for that text with other capitalization then I will see no needs as a search result. | Pass | MK 10/21/2024